## Time Plan
Product Launch Time Plan – Q4 2026
Blue cells on yellow are inputs – change them and every date, total and the timeline update automatically.
Key dates |  |  | Lead times (days)
Milestone | Date |  | Window |  |  | Days
Sourcing & PO | 2026-10-20 |  | Production / packing (PO → ship) |  |  | 8
Ship (sea / air) | 2026-10-28 |  | Transit & customs (ship → launch) |  |  | 23
Launch | 2026-11-20 |  | Total lead time (PO → launch) |  |  | 31
Re-order | 2026-12-10 |  | Selling days (launch → re-order) |  |  | 20
Products & purchase orders
Product | Order qty (units) | Unit cost min (€) | Unit cost max (€) | PO value min (€) | PO value max (€) | Sourcing & PO | Ship (sea / air) | Launch | Re-order | Re-order stock arrives (est.) | Units/day to sell out by re-order
Pet Grooming Hammock Stand Iron | 80 | 5 | 6 | 400 | 480 | 2026-10-20 | 2026-10-28 | 2026-11-20 | 2026-12-10 | 2027-01-10 | 4
Dog bark deterrent | 70 | 6 | 7 | 420 | 490 | 2026-10-20 | 2026-10-28 | 2026-11-20 | 2026-12-10 | 2027-01-10 | 3.5
Toilet paper holder stand | 50 | 5 | 6 | 250 | 300 | 2026-10-20 | 2026-10-28 | 2026-11-20 | 2026-12-10 | 2027-01-10 | 2.5
Free standing bird bath feeder | 50 | 5 | 6 | 250 | 300 | 2026-10-20 | 2026-10-28 | 2026-11-20 | 2026-12-10 | 2027-01-10 | 2.5
Total | 250 | 5.28 | 6.28 | 1320 | 1570 | [5 empty] | 12.5
Quantities and unit cost ranges provided by you. Unit costs are product cost only – shipping, customs duty, VAT and marketplace fees are not included. Per-product dates follow the key dates above; overwrite a row's date if one product moves.
Watch-outs
1. Only 8 days between PO (20 Oct) and shipping (28 Oct): confirm each supplier has stock ready, or production will push the ship date.
2. 23 days from ship to launch: realistic by air (about 5–10 days). Sea freight door-to-door usually takes 3–6 weeks, so sea risks missing the 20 Nov launch.
3. Black Friday (27 Nov) and Cyber Monday (30 Nov) fall in your first launch week – have listings and ads live before then.
4. A re-order on 10 Dec with the same ~31-day lead time arrives around 10 Jan, after Christmas. If sales start fast, bring the re-order forward.
5. Chinese New Year is 6 Feb 2027; factories close roughly late Jan to late Feb, so place any second re-order by early January.
Formulas:
Re-order stock arrives (est.) = [Re-order]+([Launch]-[Days])
Note on B6: Dates provided by you (11 Oct 2026).
Note on C17: Weighted average unit cost (min) across all products.
Note on D17: Weighted average unit cost (max) across all products.
Note on K12: Re-order date + the same total lead time (PO → launch) as the first order.

## Timeline
Timeline (weekly)
Dates come from the Key dates on the Time Plan tab. Only the Status column is edited here.
Phase | Start | End | Days | Status | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11
Sourcing & PO placed | 2026-10-20 | 2026-10-20 | 1 | Planned
Production, QC & packing | 2026-10-21 | 2026-10-27 | 7 | Planned
Shipping (sea / air) & customs | 2026-10-28 | 2026-11-19 | 23 | Planned
Listings, photos & ads set-up | 2026-10-28 | 2026-11-19 | 23 | Planned
Launch | 2026-11-20 | 2026-11-20 | 1 | Planned
Black Friday → Cyber Monday | 2026-11-27 | 2026-11-30 | 4 | Planned
Selling period (launch → re-order) | 2026-11-20 | 2026-12-10 | 21 | Planned
Re-order PO placed | 2026-12-10 | 2026-12-10 | 1 | Planned
Re-order production & shipping (est.) | 2026-12-11 | 2027-01-10 | 31 | Planned
Blue bar = phase running that week · Orange = one-day milestone · Week columns start on Monday.
Note on A10: Black Friday 2026 is Fri 27 Nov; Cyber Monday is Mon 30 Nov.

## Products
Product | Market | Local sellers | Overseas sellers | Fast (local stock) | Listings | Buyers / month | Buyers per local seller | Overseas share of sales % | Typical price | Currency | Typical price (US$) | Verdict
toilet paper holder stand | Australia | 44 | 0 | 44 | 44 | 485.2 | 11 | 0 | 29.99 | A$ | 19.35 | 44 listings deliver fast. Crowded with local stock.
toilet paper holder stand | UAE | 39 | 2 | 39 | 43 |  |  |  | 61.27 | AED | 16.68 | 39 listings deliver fast. Crowded with local stock. 2 of 43 ship from overseas.
free standing bird bath feeder | Australia | 41 | 2 | 40 | 45 | 207.9 | 5.1 | 0 | 37.99 | A$ | 24.51 | 40 listings deliver fast. Crowded with local stock. 2 of 45 ship from overseas.
free standing bird bath feeder | UAE | 42 | 5 | 42 | 47 |  |  |  | 89.99 | AED | 24.5 | 42 listings deliver fast. Crowded with local stock. 5 of 47 ship from overseas.
dog bark deterrent | Australia | 39 | 1 | 39 | 44 | 1869.3 | 47.9 | 4 | 32.99 | A$ | 21.28 | 39 listings deliver fast. Crowded with local stock. 1 of 44 ship from overseas.
dog bark deterrent | UAE | 34 | 5 | 34 | 43 | 69.3 | 2 | 0 | 72.5 | AED | 19.74 | 34 listings deliver fast. Crowded with local stock. 5 of 43 ship from overseas.
Pet Grooming Hammock Stand Iron | Australia | 25 | 22 | 24 | 47 | 277.3 | 11.1 | 100 | 39.99 | A$ | 25.8 | 24 listings deliver fast. Crowded with local stock. 22 of 47 ship from overseas.
Pet Grooming Hammock Stand Iron | UAE | 8 | 40 | 8 | 48 |  |  |  | 112.19 | AED | 30.55 | 8 listings deliver fast. Some local competition. 40 of 48 ship from overseas.